## Slide 1: Software Project Management resource allocation
Dr. D Evangelin geetha
Associate professor
Department of master of computer applications
Ramaiak institute of technology
Bangalore - 560054

## Slide 2: Learning objectives
Identify the resources required for a project
Make the demand for resources more even throughout the life of a project
Produce a work plan and resource schedule

## Slide 3: introduction
Result of resource allocation
  Activity schedule
  Resource schedule
  Cost schedule

## Slide 4: Nature of resources
Labour
Equipment
Materials
Space
Services
Time
Money

## Slide 5: Identifying resource requirements
Resource requirements list
  Stage - All
  Activity – Project Manager
  Days - 104 Days
  Quantity - 1
  Notes
  E.g

## Slide 8: Scheduling resources
Ordered list priority
  Shortest critical activity
  Critical activities
  Shortest non-critical activities
  Non-critical activity with least float
  Non-critical activities

## Slide 9: Creating critical paths

## Slide 10: Counting the cost

## Slide 11: Being specific
Availability
Criticality
Risk
Training
Team building

## Slide 12: Publishing the resource schedule

## Slide 13: Cost schedules
Staff costs
Overheads
Usage charges

## Slide 14: Scheduling sequence

## Slide 15: example
Activity | Duration (Days) | Depends on | Resource type
A | 2 | - | SA
B | 10 | A | SD
C | 2 | A | SD
D | 2 | C | SC
E | 3 | C | SC
F | 2 | C | SC
G | 4 | B, D, E, F | SA
SA – systems analyst SD-systems designer SC – Software coder
Assume that there is only one systems designer, 1 systems analyst and 2 software coder
i) Schedule the project and show your results in the form of a bar chart and resource histogram.
ii) Identify the best way of revising the plan to remove resource clashes.
Draw an activity network for the activities below. Identify critical path.